## Zc
Requirement Location | Feature | Sub Feature | Feature Description | Verification Goal | Pass/Fail Criteria | Test Type | Coverage Method | Link to Coverage
Zc 1.0.1 ace0ee | Zca | c.f* | floating point load stores shall decode as illegal | Verify that all variations of these instructions decode as illegal Cross check with instructions used in Zcmp/t | Check against ISS | Constrained-Random | Functional Coverage | TODO: Should be checked, probably in an illegal instruction test.
|  | c.* | The remaining instructions in the C extension shall be verified, follow existing C extension verification plan | Verified in C extension | N/A | N/A | N/A
| Zcb Note: For instructions with an uncompressed equivalent, check with design which are decoded to the 32b equivalent. For all others, consider a more thorough verification of the instruction, with regards to input values etc. | c.lbu | Load unsigned byte, 16-bit encoding | Register operands: All possible rs1 registers are used. All possible rd registers are used. All possible register combinations where rs1 == rd are used | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of uimm | Check against ISS | Constrained-Random | Testcase | No direct coverage, but a lot of variation is output from the debug_test2
|  | c.lhu | Load unsigned halfword, 16-bit encoding | Register operands: All possible rs1 registers are used. All possible rd registers are used. All possible register combinations where rs1 == rd are used | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of uimm | Check against ISS | Constrained-Random | Testcase | No direct coverage, but some coverage can be found in corev_rand_instr_test
|  | c.lh | Load signed halfword, 16-bit encoding | Register operands: All possible rs1 registers are used. All possible rd registers are used. All possible register combinations where rs1 == rd are used | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of uimm | Check against ISS | Constrained-Random | Functional Coverage | No direct coverage, but some coverage can be found in corev_rand_instr_test
|  | c.sb | Store byte, 16-bit encoding | Register operands: All possible rs1 registers are used. All possible rs2 registers are used. All possible register combinations where rs1 == rs2 are used | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of uimm | Check against ISS | Constrained-Random | Functional Coverage | No direct coverage, but some coverage can be found in corev_rand_instr_test
|  | c.sh | Store halfword, 16-bit encoding | Register operands: All possible rs1 registers are used. All possible rs2 registers are used. All possible register combinations where rs1 == rs2 are used | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of uimm | Check against ISS | Constrained-Random | Functional Coverage | No direct coverage, but some coverage can be found in corev_rand_instr_test
|  | c.zext.b | Zero extend byte, 16-bit encoding | Register operands: All possible rsd registers are used. | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  | c.sext.b | Sign extend byte, 16-bit encoding | Register operands: All possible rsd registers are used. | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify illegal if Zbb is not configured | Check against ISS | Constrained-Random | Functional Coverage
|  | c.zext.h | Zero extend halfword, 16-bit encoding | Register operands: All possible rsd registers are used. | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify illegal if Zbb is not configured | Check against ISS | Constrained-Random | Functional Coverage
|  | c.sext.h | Sign extend halfword, 16-bit encoding | Register operands: All possible rsd registers are used. | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify illegal if Zbb is not configured | Check against ISS | Constrained-Random | Functional Coverage
|  | c.not | Bitwise not, 16-bit encoding | Register operands: All possible rsd registers are used. | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  | c.mul | Multiply, 16-bit encoding | M_EXT=M_NONE shall result in c.mul decoding as an illegal instruction | Check against ISS | Constrained-Random | Functional Coverage
|  |  |  | Register operands: All possible rsd registers are used. All possible rs2 registers are used. All possible register combinations where rsd == rs2 are used | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
| Zcmp | cm.push | Create stack frame: store ra and 0 to 12 saved registers to the stack frame, optionally allocate additional stack space. | Verify all possible variations of rlist | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of spimm | Check against ISS | Constrained-Random | Testcase | corev_rand_interrupt++
|  |  |  | Verify instruction with watchpoint triggers on data address | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify exception behaviour, no following bus transaction: if a sub-operation triggers an exception, no further transaction shall arrive on the bus originating in the trapped instruction Note: this functionality is closely matched with items mentioned in other features of the 40s, such as PMP/PMA. Synchronize verification effort to avoid double work. | Assertion Check | Constrained-Random | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.u_zc_assert.a_multiop_exception_stop_dbus_push
|  |  |  | Verify exception behaviour, partially completed state shall match ISS: when a multi-operation instruction is stopped by an exception, state can have changed. Verify against ISS. Note: 40s implementation follows the example sequence in the Zc spec. ISS's should match this. (the order might change) Coverage note: cross between possible register lists and exception arriving between/at all sub-operations would be optimal | Check against ISS | Directed Non-Self-Checking | Testcase | Coverage hole, evaluate priority
|  | cm.pop | Destroy stack frame: load ra and 0 to 12 saved registers from the stack frame, deallocate the stack frame. | Verify all possible variations of rlist | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of spimm | Check against ISS | Constrained-Random | Functional Coverage | corev_rand_interrupt++
|  |  |  | Verify instruction with watchpoint triggers on data address | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify exception behaviour, no following bus transaction: if a sub-operation triggers an exception, no further transaction shall arrive on the bus originating in the trapped instruction Note: this functionality is closely matched with items mentioned in other features of the 40s, such as PMP/PMA. Synchronize verification effort to avoid double work. | Assertion Check | Constrained-Random | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.u_zc_assert.a_multiop_exception_stop_dbus_pop
|  |  |  | Verify exception behaviour, partially completed state shall match ISS: when a multi-operation instruction is stopped by an exception, state can have changed. Verify against ISS. Note: 40s implementation follows the example sequence in the Zc spec. ISS's should match this. Coverage note: cross between possible register lists and exception arriving between/at all sub-operations would be optimal | Check against ISS | Directed Non-Self-Checking | Testcase | Coverage hole, evaluate priority
|  | cm.popret | Destroy stack frame: load ra and 0 to 12 saved registers from the stack frame, deallocate the stack frame, return to ra. | Verify all possible variations of rlist | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of spimm | Check against ISS | Constrained-Random | Functional Coverage | corev_rand_interrupt++
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify exception behaviour, no following bus transaction: if a sub-operation triggers an exception, no further transaction shall arrive on the bus originating in the trapped instruction Note: this functionality is closely matched with items mentioned in other features of the 40s, such as PMP/PMA. Synchronize verification effort to avoid double work. | Assertion Check | Constrained-Random | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.u_zc_assert.a_multiop_exception_stop_dbus_popret
|  |  |  | Verify exception behaviour, partially completed state shall match ISS: when a multi-operation instruction is stopped by an exception, state can have changed. Verify against ISS. Note: 40s implementation follows the example sequence in the Zc spec. ISS's should match this. Coverage note: cross between possible register lists and exception arriving between/at all sub-operations would be optimal | Check against ISS | Directed Non-Self-Checking | Testcase | Coverage hole, evaluate priority
|  | cm.popretz | Destroy stack frame: load ra and 0 to 12 saved registers from the stack frame, deallocate the stack frame, move zero into a0, return to ra. | Verify all possible variations of rlist | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify all possible variations of spimm | Check against ISS | Constrained-Random | Functional Coverage | corev_rand_interrupt++
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify exception behaviour, no following bus transaction: if a sub-operation triggers an exception, no further transaction shall arrive on the bus originating in the trapped instruction Note: this functionality is closely matched with items mentioned in other features of the 40s, such as PMP/PMA. Synchronize verification effort to avoid double work. | Assertion Check | Constrained-Random | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.u_zc_assert.a_multiop_exception_stop_dbus_popretz
|  |  |  | Verify exception behaviour, partially completed state shall match ISS: when a multi-operation instruction is stopped by an exception, state can have changed. Verify against ISS. Note: 40s implementation follows the example sequence in the Zc spec. ISS's should match this. Coverage note: cross between possible register lists and exception arriving between/at all sub-operations would be optimal | Check against ISS | Constrained-Random | Functional Coverage | Coverage hole, evaluate priority
|  | cm.mva01s | Move a0-a1 into two registers of s0-s7 | Verify all possible variatons of sreg1, sreg2. Note that sreg1 = sreg2 is illegal | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify exception behaviour, no following bus transaction: if a sub-operation triggers an exception, no further transaction shall arrive on the bus originating in the trapped instruction Note: this functionality is closely matched with items mentioned in other features of the 40s, such as PMP/PMA. Synchronize verification effort to avoid double work. | Assertion Check | Constrained-Random | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.u_zc_assert.a_multiop_exception_stop_dbus_mva01s
|  |  |  | Verify exception behaviour, partially completed state shall match ISS: when a multi-operation instruction is stopped by an exception, state can have changed. Verify against ISS. Note: 40s implementation follows the example sequence in the Zc spec. ISS's should match this. Coverage note: cross between possible register lists and exception arriving between/at all sub-operations would be optimal | Check against ISS | Directed Non-Self-Checking | Testcase | Coverage hole, evaluate priority
|  | cm.mvsa01 | Move two s0-s7 registers into a0-a1 | Verify all possible variatons of sreg1, sreg2. | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Check against ISS | Directed Non-Self-Checking | Testcase | Covered in directed test "zc_test"
|  |  |  | Verify exception behaviour, no following bus transaction: if a sub-operation triggers an exception, no further transaction shall arrive on the bus originating in the trapped instruction Note: this functionality is closely matched with items mentioned in other features of the 40s, such as PMP/PMA. Synchronize verification effort to avoid double work. | Assertion Check | Constrained-Random | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.u_zc_assert.a_multiop_exception_stop_dbus_mvsa01
|  |  |  | Verify exception behaviour, partially completed state shall match ISS: when a multi-operation instruction is stopped by an exception, state can have changed. Verify against ISS. Note: 40s implementation follows the example sequence in the Zc spec. ISS's should match this. Coverage note: cross between possible register lists and exception arriving between/at all sub-operations would be optimal | Check against ISS | Directed Non-Self-Checking | Testcase | Coverage hole, evaluate priority
| Zcmt Note: Deprioritize as this is furthest from ratification | cm.jt | jump via table without link | Verify all possible variations of index | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Assertion Check | ENV capability, not specific test | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.core_i.controller_i.controller_fsm_i.controller_fsm_sva.a_no_sequence_interrupt
|  |  |  | Verify all table jump-related fetches are checked by PMP/PMA. Specifically break/follow the rules for both systems | Check against ISS | Directed Non-Self-Checking | Testcase | Coverage hole, evaluate priority
|  | cm.jalt | jump via table and link to ra | Verify all possible variations of index | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | Verify interrupts(maskable and non-maskable), debug and single stepping can not stop execution after the instruction has started to change state. Make sure external interrupts happen at all stages of execution. Expect atomic execution | Assertion Check | ENV capability, not specific test | Assertion Coverage | A: uvmt_cv32e40s_tb.dut_wrap.cv32e40s_wrapper_i.core_i.controller_i.controller_fsm_i.controller_fsm_sva.a_no_sequence_interrupt
|  | JVT CSR | Table Jump base vector and control register | csr stateen bit 2 controls user mode access, if bit is not set, cm.jt and cm.jalt should decode as illegal. Access also controlled with smstateen, illegal if not enabled. | Check against ISS | Directed Non-Self-Checking | Testcase | Coverage hole, evaluate priority
|  |  |  | JVT is used as base for jt/jalt | Check against ISS | Constrained-Random | Functional Coverage | Imperas generated coverage, hierarchy path: uvmt_cv32e40s_tb.imperas_dv.idv_trace2cov.cov_1.obj_[instr]
|  |  |  | JVT can be used to swap jump tables | Check against ISS | Constrained-Random | Code Coverage | N/A
-------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- END -----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------

## DONOTDELETE
Pass/Fail Criteria | Test Type | Coverage Method
Self Checking Test | RISC-V Compliance | Testcase
Signature Check | OpenHW Compliance | Functional Coverage
Check against ISS | Directed Self-Checking | Assertion Coverage
Assertion Check | Directed Non-Self-Checking | Code Coverage
Any/All | Constrained-Random | N/A
Other | ENV capability, not specific test
N/A | Other
N/A

## References
Reference Name | Full Name of Reference Document | URL | Git Hub Hash (if appropriate)
OBIv1.4 | Open Bus Interface (OBI) Specification, v1.4, 3/8/2022 | https://github.com/openhwgroup/core-v-docs/blob/master/cores/obi/OBI-v1.4.pdf | 4fdcf97be297201398f6abdd0bfca5e1e1d76440
UM 40205f | CV32E40S User Manual | https://docs.openhwgroup.org/projects/cv32e40s-user-manual/en/0.4.0/index.html | 40205ff125fde4e8f0d3512b83170021fc8309f5
Zc 1.0.1 ace0ee | Zc specification | https://github.com/riscv/riscv-code-size-reduction/tree/main/Zc-specification | ace0ee0328f7de316a84d17b528e20b8fd28df3e