## Sheet1
URL of Verification Plans: | https://github.com/openhwgroup/core-v-docs/tree/master/verif/CV32E40P/VerificationPlan
Directory | Vplan | Status | Reviewer(s) | Comment
Base Instruction Set | Counters | Needs update | Paul Z | Lots of updates to the UM since this was captured
| RV32I | Ready for Review
| RV32C | Ready for Review | Arjan B
| RV32M | Ready for Review | Arjan B
| RV32Z | Ready for Review | Arjan B
| Exceptions | Ready for Review | John Martin
custom_circuity | prefetch unit | Needs capture |  | May not be required
debug-trace | Debug | Reviewed | Paul Z
| External Debugger | Out of scope
interrupts | none | Needs capture |  | Is this section of the UM up-to-date?
privileged_spec | CSRs | Needs capture
| Privileged Instructions | Needs capture |  | ecall, ebreak, wfi, etc.
| Modes | Out of scope |  | Covered by Interrupts, Debug, CSRs for CV32E40P
physical_interfaces | Sleep Unit | Needs capture
| Configuration and Control | Needs capture
| APU | Out of scope
| OBI | Ready for Review | Arjan B
xpulp_instruction_extensions | bit_manipulations | Not certain |  | Captured before decision to defer Xpulp instruction verification. Almost certainly out of date wrt to the latest UM.
| general_alu | Not certain
| Immediate-branching | Not certain
| hwloop | Not certain
| packed-simd | Not certain
| Pulp-cluster | Not certain
| Xpulp-postinc-loadstore | Not certain